British Sign Language (BSL) Progress Report 2020

Fife College

British Sign Language (BSL) Progress Report 2020

# Table of Contents

Table of Contents	2

SECTION 1:	3

Introduction	3

Section 2	4

Fife College BSL Action Plan update 2020	4

Section 3	16

Plans for the next for years	16

Section 4	17

FE/HE Institutions – Progress Report	17

# SECTION 1:

# Introduction

The BSL National Plan, published 24 October 2017, was developed through extensive engagement with Deaf and Deafblind BSL users and those who work with them.

As requested by the BSL (Scotland) Act 2015, Fife College first published their BSL Plan in October 2018 which sets out our actions which we will strategically deliver over the period 2018 – 2024 and is framed around the relevant long term goals as detailed in the BSL National Plan.

This plan aims to ensure equal access to services and support for BSL users at Fife College.  As stated in the Fife College Regional Outcome Agreement and the Access and Inclusion Strategy.

Fife College is committed to working with people who are D/deaf and Deafblind in order to support their contribution to the Fife College plan by consulting with BSL users and working towards protecting and supporting BSL, including in its tactile form.

Fife College will continue to engage with its partners and this include Fife Council, Deaf Action, Opportunities Fife, Skills Development Scotland, Fife College Student Association, NHS Fife, BSL users and their representatives during the implementation of the plan with ongoing monitoring.

# Section 2

# Fife College BSL Action Plan update 2020

| Outcome 1: Scottish Public Services – Across the Scottish public sector, information and services will be accessible to BSL users* |
| --- |
| BSL National Actions | Strategy for implementation | Timescale | Evaluate | Progress |
| [Action 2] Analyse existing evidence we have about students and prospective students who use BSL in our college; identity and fill key information gaps so that we can establish baselines and measure our progress. | We will do this by analysing trends in public data (i.e. Scottish census), looking at previous student engagement, investigating areas that BSL users feel are barriers to them attending Fife College, analyse BSL student performance indicators and also speaking with partner organisations about their experiences. | Ongoing | Feedback from student who are BSL users by providing BSL survey or consultation forum. | By attending the BSL Implementation Group (BSLIG) we have been able to speak with partner organisations about their experiences. When working with our partners we have been able to share the experiences of our students who use BSL in College. However, there has been a lack of students who are BSL users in last 2 years which has made it difficult to analyse student performance indicators. |
| [Actions 3, 4] Improve information and services for students and prospective students who use BSL, including making our website more accessible to BSL users. | This will be done by producing guidance documents and videos for BSL students on the application process, funding process, wellbeing and Inclusion. We will also ask BSL users to help us identify any changes that may be required to our website to make it more accessible to the BSL community. | Partial Completion | Continuous consultation regarding correct policy and procedures BSL version made available on line including website updates. | In partnership with Deaf Community Services 5 videos were created and signed in BSL by members of the BSL Community. These included “Welcome to Fife College Inclusion Team” and “ Fife College Health and Wellbeing” We continue to work on this action point by creating more information videos. |
| [Action 5] Promote the use of the Scottish Government’s nationally funded BSL online interpreting video relay services called ‘contact SCOTLAND-BSL’, which allows BSL users to contact public and their sector services and for these services to contact them. | By inviting ‘contactSCOTLAND-BSL’ to do awareness sessions for all front line staff and repeat these sessions each year for staff working with BSL users. | Complete with annual training | Staff feedback. | We have continued to promote the use of contact SCOTLAND-BSL with all front of house staff with iPads also being installed on all reception desks. Almost all Student Experience and Engagement staff have taken part in contact SCOTLAND-BSL awareness sessions. We will also add contact SCOTLAND-BSL, tab to the college website. |
| [Action 6] Signpost staff who work with BSL users to appropriate BSL awareness training and enable them to take up such training. | By making sure training materials are available on the Fife College staff gateway, we will also promote the accredited Level 1 and 2 BSL course at Fife College. | Ongoing | Data collection on class numbers and retention rates. | In academic year 19-20, 7 Fife College staff undertook the BSL Level 1 qualification, 3 staff members undertook BSL Level 2 and 1 staff member was enrolled on the newly introduced BSL Level 3 qualification. Due to COVID-19 these courses are ongoing into academic year 20-21. |

| Outcome 2: Family Support, Early Learning and Childcare - “The Getting it Right for Every Child (GIRFEC) approach will be fully embedded, with a D/deaf or Deafblind child and their family offered the right information and support at the right time to engage |
| --- |
| BSL National Actions | Strategy for implementation | Timescale | Evaluate | Progress |
|  | Ensure that current and potential students have access to information in BSL regarding funding for childcare. Work collaboratively with our partners to identify families who may require BSL training by offering information and support on accessing our provisions. | Ongoing Ongoing | Continues reviewing of funding to ensure correct information supported by feedback from BSL Users and funding team. Feedback from partners regarding correct provision provided. | To compliment the new Fife College online funding application form, information in BSL will be recorded in 2021 to explain the new online system. Due to the low number of applicants who are BSL users this has not been required however the provision is still available as needed. |
| Outcome 3: School Education - “Children and young people who use BSL will get the support they need at all stages of their learning, so that they can reach their full potential; parents who use BSL will have the same opportunities as other parents to be fully involved in their child’s education; and more pupils will be able to learn BSL at school” |
| BSL National Actions | Strategy for implementation | Timescale | Evaluate | Progress |
|  | In conjunction with Fife College Developing Young Workforce (DYW) Partnership team we will ensure a tighter transition process for young BSL users leaving school. This will include an extended transition, awareness sessions for new staff and facilitating interpreting services as and when required in partnership with the Deaf Communication Services. | October 2020 | Feedback from BSL Users on their transition journey. | Due to the low number of applicants who are BSL users this has not been required however the provision is still available as needed. |
|  | We will also explore how Fife College can work in partnership with local High Schools to offer BSL as a curriculum choice within our School College Partnership. | Ongoing |  | This action is currently on hold due to COVID-19. However, we currently have one S4 pupil, who is deaf studying level 2 BSL in place of a language requirement at school. Feedback from this student has been very positive. |
| Outcome 4: Post-School Education - “BSL users will be able to maximise their potential at school, will be supported to transition to post-school education if they wish to do so, and will receive the support they need to do well in their chosen subject(s)” |
| BSL National Actions | Strategy for implementation | Timescale | Evaluate | Progress |
| [Action 25] We will take action to ensure that students and prospective students who use BSL are properly supported | Providing accessible information about what BSL users can expect from the college. Full access to open days for prospective students who use BSL. Support throughout the student journey for students who use BSL (including completing application forms, interviews, applying for Disabled Students Allowance etc.) Support during the transition process, which needs to be agreed between the school and college. Access to information within the college campus. Provide an interpreter for Graduation, and if requested, provide a recording on the Fife College Website. | Ongoing Ongoing Complete October 2021 September 2024 Complete | Feedback from BSL users. Feedback from student association. End of year evaluation and consultation with BSL users. Feedback from BSL Users on their transition journey. Consultation with students and partnership organisations. Feedback after the event. | Information videos regarding Inclusion and Health and Wellbeing have been created. Welcome to Fife College video to be produced Unfortunately due to COVID-19 open days were virtual this year and as such we were unable to provide an interpreter however subtitles were made available. By working closely with DCS Interpreters are readily available on request for any student that requires them. Due to the low number of applications from students who are BSL Users this has not been required however is available on request. Working with digital services to have BSL videos displayed on information screens over all campuses No requests have been made for an interpreter so far however the graduation ceremony was recorded and uploaded to the college website with closed captioning. |
| [Action 26] Take on board guidance/advice produced by the SFC and others to ensure that across the college, staff are aware of their responsibilities towards BSL users, and that students who use BSL know what to expect. [Action 27] Provide assistance (including examples) to students who use BSL to help complete SAAS application forms. | Invite continuous feedback from students/prospective students and staff who use BSL over the coming year/18 months after adopting this plan. Commit to reviewing/refreshing this plan which includes more ‘local’ actions (based on that feedback) after the national progress report (due October 2020). By working with Deaf Community Services to provide interpreters to work with Fife College staff and the student to complete SAAS application forms. | Ongoing October 2020 Complete | Survey monkey, consultation and student survey. Student feedback. | We currently only have one BSL User enrolled at Fife College, we regularly seek their feedback on how can improve going forward. Continue to work with partners This action is completed as required. Interpreters are available on request. |

| Outcome 5: Training, Work and Social Security - “BSL users will be supported to develop the skills they need to become valued members of the Scottish workforce, so that they can fulfil their potential, and improve Scotland’s economic performance. They will be provided with support to enable them to progress in their chosen career” |
| --- |
| BSL National Actions | Strategy for implementation | Timescale | Evaluate | Progress |
| [Action 35] Raise awareness of the UK Government’s ‘Access to Work’ scheme for students who use BSL towards the end of their course, so that they can benefit from the support it provides when they enter the world of work. | We will work in partnership with the Fife College Employability & Partnerships Team to signpost students to a range of information, advice and guidance in BSL. A BSL interpreter will also be provided, if requested, for exit reviews. We will also work with employers to provide advice on the needs of BSL users. | Ongoing | Feedback from employability Team regarding how often the service is accessed by BSL users. | Present BSL student are continuing with their studies |

| Outcome 6: Health (including social care), Mental Health and Wellbeing - “BSL users will have access to the information and services they need to live active, healthy lives and to make informed choices at every stage of their lives” |
| --- |
| BSL National Actions | Strategy for implementation | Timescale | Evaluate |  |
|  | Take steps to ensure that health/mental health services (including advice and counselling services) within the college/university are fully accessible to students who use BSL. Ensuring web pages are accessible to BSL users and ensure visibility for users of BSL. Ensuring the service is accessible through use of Contact Scotland/having BSL interpreters available. Ensure that Fife College’s recently employed Mental Health Adviser has access to information and priority for future training sessions. | Complete October 2021 Complete | Feedback from Student BSL users. Student survey available in BSL version. Staff evaluation and CLPL record. | Mental health and wellbeing video has been created in BSL and will be uploaded to the Fife College website. In partnership with Fife Council Deaf Community services, BSL Interpreters are readily available. By 2021 almost all promotional materials will have closed captions available. All relevant training is up to date. Annual refresher training given. |

| Outcome 8: Culture and the Art - “BSL users will have full access to the cultural life of Scotland, an equal opportunity to enjoy and contribute to culture and the arts, and are encouraged to share BSL and Deaf Culture with the people of Scotland” |
| --- |
| BSL National Actions | Strategy for implementation | Timescale | Evaluate |  |
|  | Take action to ensure that extracurricular/recreational activities offered within the college/university are accessible to students who use BSL. Ensuring that Fife College continue to promote their culture of Inclusivity and ensuring that all activities are accessible to all. | Complete Complete | Student survey and feedback from Fife College Student Association. Feedback from Fife College Student Association. | Fife College Student Association have continued to promote Inclusion by having a number of their video’s in BSL, also promoting BSL and encouraging students to learn. Students who are BSL Users are offered an interpreter for social events such as fresher’s week and the award ceremonies however due to the low number of students who are BSL users this offer has not been accepted as yet. |

| Outcome 10: Democracy - “BSL users will be fully involved in democratic and public life in Scotland, as active and informed citizens, as voters, as elected politicians and as board members of our public bodies” |
| --- |
| BSL National Actions | How will we implement | Timescale | Evaluate |  |
|  | Work in partnership with Fife College Student Association (FCSA) to ensure that all inter-college elections are accessible to BSL users, having interpreters for commencement speeches and/or election campaigns. Encouraging BSL users to be involved with Fife College Culture including class representatives and FCSA volunteers. | Complete Ongoing | Feedback from Fife College Student Association. | FCSA election manifestos were made accessible for BSL users. All videos were signed and published on relevant platforms. This continues to be ongoing throughout the academic year. |

# Section 3

# Plans for the next for years

Fife College and partner agencies will endeavour to meet all the recommendations of the BSL National Plan.

Fife College, in partnership with Deaf Communication Services, will continue to attend quarterly open meetings where Deaf people are encouraged to come and share their views on how to improve the plan and what is important to them.

One of the biggest challenges Fife College face is low numbers of BSL users enrolling on courses. For academic year 20-21 we potentially have 4 students who are BSL users on full time programmes.

# Section 4

# FE/HE Institutions – Progress Report

- Progress of your FE/HE’s Institution’s BSL Plan

a.   	Since the implementation of your institution’s BSL plan, which action points have progressed?

b.   	Which action points have been more difficult to progress?

c.   	How have you promoted your BSL plans to students and prospective students?

Since the implementation of the BSL Plan, Fife College has worked in partnership with BSL Implementation Group to progress the action points in the tables in section 3. The action points that we have been unable to progress have been caused by a lack of BSL Users enrolled at college, COVID19 and lack of engagement from the D/deaf Community. We had hoped to progress outcome 3 by working in conjunction with Fife College Developing Young Workforce (DYW) Partnership team to ensure a tighter transition process for young BSL users leaving school. However, due to lack of applications this will be an ongoing action. The BSL plan is available on the Fife College website and is discussed at all BSL Implementation Group meetings, which has representatives of the D/deaf community as members

- Challenges and Gaps

- What challenges have you faced towards implementing your institution’s BSL plan, and how did you address them?

- Do you feel that there are gaps arising from your institution’s BSL plan? If yes, please detail what they are.

Lack of students meant that there was limited student input. While filing and producing the videos for Fife College and Fife Council the BSLIG members who were representatives of the D/deaf community asked that the videos be filmed with BSL users rather than interpreters, this led to delays as it was challenging to find volunteers and additional time was required for the scripts to be translated. One of the volunteers that came forward was deafblind therefore the process was more challenging as the scripts firstly had to be transposed into Braille before then being memorised and translated into BSL by the volunteer. We also had limited access to the recording studio facilities and cameraman as these were only free during the college breaks. Due to COVID19 the BSL classes for level 1, 2 and 3 had to be postponed however these will be restarted in September. Due to the implementation of the BSL plan there is much more awareness of the college’s commitment to the D/deaf community and therefore every eventuality is taken into consideration which in turn reduces any gaps that may arise.

- BSL-signing Students

- Have you received any feedback from BSL students about your institution’s BSL plan?

- If yes, please provide a summary and what methods they used?

- If no, what do you think contributed to this?

Due to only having one BSL student last year, we used the quarterly meetings arranged by Fife Council to gain feedback. However, moving forward we hope this will change.

- Future Actions and Plans

- What actions are still required to be achieved from your institution’s BSL Plan?

- What future additions & changes will be implemented in your institution’s BSL Plan?

- What future engagement activities do you have planned with your BSL students?

A number of actions will remain ongoing due to the ever changing demands and culture within the college. This will allow us to complete annual training, improve services and produce more BSL information videos. At present no future additions or changes will be implemented unless a gap is identified within the national progress reports. Before the end of the year we hope to gain the views of our new BSL students, by use of Survey Monkey we hope to identify our strengths and weaknesses and pinpoints any areas of improvement. All Student Advisers are aware that interpreters are available on request and that these can be booked for any student activities.

- FE/HE Institutions

- Did you work with other FE/HE institutions, BSL Lead Officers & Public Bodies to provide and receive support in implementing your BSL plan?

- If yes, please provide a summary.

- Has your institution's Outcome Agreement been updated to reflect their corresponding BSL Plan?

Partners Involved in the BSL Implementation group organised by Fife Council Social Care Partnership are: B.S.L Representatives Fife Council Education Services Sensory Support (Deaf) Service NHS Fife Equality and Human Rights Team Fife’s Health and Social Care Partnership Deaf Communication Service Fife College Scotland’s Rural College (SRUC) Fife Council: Communities and Neighbourhood Team ONFife The Fife College Outcome Agreement has been updated to reflect the BSL Plan, which in turn incorporates the work which is completed with the other agencies.

- Deaf Action

a: Do you feel you have a good understanding of Deaf Action’s role in supporting FE/HE institutions with their BSL Plans?

b: Is there any specific support that you would like to receive from the BSL Officers at Deaf Action, and to what extent?

Deaf Action have been extremely supportive and informative in the creation of the BSL plan. We do not feel that there is any specific support required at this time however if there are any gaps in the plan we would request support with addressing these.